## Sheet 1
| summary | description | created
1 | IE 11 - User Profile - Pregnancy checkbox at times will not retain it's selection | When attempting to uncheck the pregnancy checkbox after selecting it, it was found that sometimes the checkbox would not take in IE 11. This issue does not occur in firefox and chrome. Steps to reproduce: 1. Navigate to application on IE 11. 2. Sign In. 3. Select User profile icon. 4. Select Pregnancy checkbox. 5. Select Rex icon to return to drug cabinet. 6. Select user profile icon. 7. Uncheck the pregnancy checkbox. 8. Return to drug cabinet. 9. Return to user profile. 10. Note that the checkbox will be checked. | 2015-07-02T16:48:59.000-0400
2 | Android - Add Drug Modal will sometimes auto focus on the year field causing it to display first | At times the Add Drug modal on Android when launched will display the year selection list on top of it. It seems to be a focus issue, although that is not the field that we are focusing on. Steps to reproduce: 1. Navigate to application on Android Chrome. 2. Sign In. 3. Add a drug via the "+" icon. 4. Search for a drug and add it to the cabinet 5. Note that the year field will sometimes be displayed instead of the Add Drug Modal first.. | 2015-07-02T13:54:03.000-0400
3 | Mobile Safari/Chrome/Firefox - Sign In Screen will place focus on email field causing keyboard display | When viewing the sign in screen on iOS and android, the email field is being focused by default. On iOS this behavior is strange b/c the user will select email and then the keyboard will appear and then disappear. Selecting email again will cause it to work just fine. Steps to reproduce: 1. Navigate to application. 2. Select Sign In. 3. Note on Android the keyboard will just appear. 4. On iOS, select the email field. 5. Note the keyboard will display and then disappear again as if to lose focus. 6. Select email again and then everything will be fine. | 2015-07-02T13:36:32.000-0400
4 | Add Drug - Adding a drug that returns multiple results that are exact matches results in all displaying In Cabinet when selected | When adding a drug that has multiple exact matches in the result, selecting any others in the list will also display that they are "In Cabinet". Steps to reproduce: 1. Navigate to application. 2. Sign In. 3. Select Add Drug "+" icon. 4. Search for prednisone. 5. Select a prednisone that has multiple exact copies. 6. Add to Cabinet on that prednisone. 7. Go back to results. 8. Select a different prednisone that is spelled the same. 9. Note that it will display In Cabinet. | 2015-06-30T20:21:20.000-0400
5 | Drug Cabinet - On mobile, when adding drugs to the cabinet and then signing out and signing in, the drug cabinet is empty | On both mobile Safari and Chrome, logged in as a user and added drugs to the cabinet. Logged out and then logged back in with the same username. The drugs cabinet is empty. | 2015-06-30T18:33:23.000-0400
6 | Session timeout takes user to landing page but the Hi "username" text and profile icon are still present | Upon session timeout, the user is taken back to the landing page. Only issue is that the user profile data is still displayed at the upper left hand corner. The "Hi <username>" and profile icon are still displayed. Steps to reproduce: 1. Navigate to application. 2. Sign In. 3. Wait for session timeout. 4. Click on an action on the page. | 2015-06-30T17:41:19.000-0400
7 | SIgn In - When sign in is unsuccessful shows an error message and returns to landing page | Steps to reproduce: 1) Try to sign in with a wrong password 2) After the error message user will be in the landing page. | 2015-06-30T17:24:38.000-0400
8 | Sign Up screen: Incomplete email addresses are allowed | In the sign up screen email addresses without the '.com' or '.net' are allowed without any error message. (example: aa@bb) In the previous versions this wasn't allowed. | 2015-06-30T13:54:31.000-0400
9 | Sign In - On Mobile Safari/Chrome/Firefox, unable to Sign In with a valid user | When attempting to sign in with an existing user through Mobile Chrome/Firefox/Safari, an "incorrect password" response keeps being returned. After talking to Lauren this is a generic message that we are throwing back. Currently we sign in to the QA environment through a mobile browser. I have tried various logins that are working through the desktop browser but are not working through mobile browsers. Steps to reproduce: 1. Navigate to application. 2. Attempt to Sign In with a working account (can sign in through desktop application.) 3. Note that you won't be able to sign in and incorrect password will be displayed. | 2015-06-30T12:54:46.000-0400
10 | Expired drugs expiration date not shown in red | Steps to reproduce 1Log in and go to my drug cabinet 2)Click on add new drug 3)Add new drug with the expiration date in the past 4)Go back to my drug cabinet 5)The expiration date is NOT shown in red | 2015-06-30T08:41:16.000-0400
11 | In IE11 when a new user adds new drugs only one is shown | Steps to reproduce: 1) Go to sign up and create a new user 2)In my drug cabinet add four drugs without leaving the screen 3)go back to my drug cabinet 4)Only one drug is shown 5)Press F5 6) Now all drugs are shown | 2015-06-30T08:37:34.000-0400
12 | Purchase certificate for HTTPS support | Acquire server certificate to implement HTTPS on server. | 2015-06-29T19:42:44.000-0400
13 | Recall drugs sometimes are not marked in red. | Step to reproduce: 1) Login into the application and add a drug with recall (niacin, dopamine) 2) GO back to My drug cabinet 3) Sometimes the recalls are shown and some others are not. Happens more often in IE 11 See attachment | 2015-06-29T19:26:52.000-0400
14 | Scroll bar under expiration date screen | When the expiration screen opens in any browser there's a scroll bar under it Steps to reproduce: 1) Go to my drug cabinet 2) Click in Add a drug 3) Search for a drug and click on "Add to my cabinet" 4) When the expiration screen opens the scroll bar is there .See attachment | 2015-06-29T19:02:40.000-0400
15 | iPhone 5 or 320p browser width - My Drug Cabinet "+" icon overlays on top of text | When viewing My Drug Cabinet on the iPhone 5 or a desktop browser at 320p width, the "+" icon is on top of the text My Drug Cabinet. See attached screenshot. Steps to reproduce: 1. Navigate to application on an iphone 5 or browser at 320p width. 2. Sign In. 3. Note the "+" icon is displayed over top of the "My Drug Cabinet" copy. | 2015-06-29T16:20:20.000-0400
16 | My Profile - Pregnancy copy has misalignment issues when degraded to various viewport sizes | When degrading the My Profile page with the pregnancy copy that is now present, there is misalignment of text at various viewport sizes. Attached are screenshots at 320p, 480p and 640p browser width. Steps to reproduce: 1. Navigate to the application. 2. Sign In. 3. Select My Profile icon in the upper right hand corner. 4. Set viewport size to 320p, 480p or 640p. 5. Note the alignment issues with the pregnancy text. | 2015-06-29T16:08:18.000-0400
17 | IE11 - Drugs are not shown in the cabinet until the screen is refresh | Steps to reproduce: Prerequisites: Have an account with at least one drug in the cabinet 1) Log in with the account 2) Only the box with the "Add a drug" box is shown 3) Press F5 4) Now all drugs are shown. See attachment | 2015-06-29T15:46:19.000-0400
18 | Favicon is not shown in IE 11 until user logs in | Favicon works fine in Chrome and Firefox but it's not shown in IE 11 until the user logs in or logs out. | 2015-06-29T15:18:49.000-0400
19 | Drug Details - When viewing different tab information, the browser will jump to the top of the screen | When viewing different drug detail information on a mobile or a non-maximized desktop browser, switching between the tabs causes the page to jump to the top. This can create a negative experience for the user when they wish to just read the information. This is especially annoying on mobile where the user constantly has to scroll down to read what they want. Steps to reproduce: 1. Navigate to the application on a mobile browser or a desktop (sized so that you have to scroll to view the full page). 2. Sign in. 3. Select Add Drug "+" 4. Search for a valid drug (i.e. Advil) 5. View it's drug details. 6. Click on some of the other tabs of the details. 7. Note that it will jump to the top of the page everytime you select a different tab. | 2015-06-29T13:30:01.000-0400
20 | Add Drug - When doing a search for a drug that has no results, no indication given to user that search is done and no results | In previous builds, we did inform the user when doing a drug search and no results were found. In the most recent QA build, this information is no longer being displayed to the user. The user is presented with a loading icon when they initiate the search but than nothing is displayed after this point. Steps to reproduce: 1. Navigate to application. 2. Sign in. 3. Select Add Drug "+" 4. Search for an item that will return no results (i.e. "Seef) 5. Note there is no copy to the user that there are no results. | 2015-06-29T13:25:03.000-0400
21 | iOS Tablets - Expiration Date control does not have button to set the date | When testing the expiration date feature of Add Drug on an iOS Tablet (iPad and iPad mini), the date control appears as a pop up control with no means to set the date. See attached screenshot. Steps to reproduce: 1. Navigate to the application on an iOS tablet. 2. Sign in. 3. Select Add Drug button. 4. Search for a drug. 5. Tap on the drug name. 6. Tap Add to Cabinet button. 7. Add Drug modal will appear. 8. Select the Expiration date field. 9. Note that the pop-up will appear with no means of selecting the date. | 2015-06-29T10:34:45.000-0400
22 | Mobile Chrome - Add Drug Modal - Selection from Expiration date control does not display correctly | When adding expiration date in mobile chrome, when the date is populated the UI display of it is not correct. See attached screenshot. Steps to reproduce: 1. Navigate to the application on mobile chrome. 2. Sign in. 3. Select Add Drug button. 4. Search for a drug. 5. Tap on the drug name. 6. Tap Add to Cabinet button. 7. Add Drug modal will appear. 8. Select the expiration date field. 9. Select a date from the calendar controls and set it. 10. Note the UI display of the date in the field. | 2015-06-29T10:18:06.000-0400
23 | Expiration date is not working in Firefox and IE browsers | Steps top reproduce: 1) Open Rex in Firefox 2) Go to My drug cabinet and add a new drug. 3) Enter the expiration date. 4) Expiration date is now shown , even if you log with the same user in different Browser 5) Repeat steps 1) to 4) with IE browser. Same results Expiration date works fine in Chrome | 2015-06-28T21:10:25.000-0400
24 | My Drug Cabinet - Drugs in cabinet with expiration date data with browser width at 480p or below result in text overlap | When viewing the drug cabinet that has a drug with an expiration date value attached, at 480p width or below the drug name and expiration values or overlapped. See attached screenshot. | 2015-06-28T19:45:31.000-0400
25 | iOS Phone Safari - Selecting Expiration Date in date picker does not actually populate date field | When selecting the expiration date from the date picker on Safari on iOS Phone, setting the date does not actually populate the date field. Hitting Add Drug will still add the date even though it is not visible to the user. Steps to reproduce: 1. Navigate to the application on a mobile device. 2. Sign in. 3. Select Add Drug button. 4. Search for a drug. 5. Tap on the drug name. 6. Tap Add to Cabinet button. 7. Add Drug modal will appear. 8. Tap into Expiration field. 9. Select the desired date and select done. 10. Note that the date values will not be populated in the field. 11. Saving the drug and going back to the cabinet will display the expiration date information. | 2015-06-28T19:41:26.000-0400
26 | Desktop Firefox - Add Drug modal display maximized and at to the top of the page creating a strange appearance | When attempting to view expiration date the Add Drug Modal on desktop firefox, it was found that the modal appeared incorrect. See attached screenshot. Steps to reproduce: 1. Navigate to the application on desktop firefox. 2. Sign in. 3. Select Add Drug button. 4. Search for a drug. 5. Tap on the drug name. 6. Tap Add to Cabinet button. 7. Add Drug modal will appear. 8. Note that the modal will appear at the top of the screen completely taking up width of browser window. | 2015-06-28T19:36:07.000-0400
27 | Add Drug - Find Icon alignment is off on mobile devices | When viewing the Add Drug page, the new find icon is not aligned correctly when the pixel width of the browser is 480p and below. See attached screenshot. Steps to reproduce: 1. Navigate to application with mobile browser (or set desktop to 480 or 320 pixel width) 2. Sign In 3. Select "+" icon to Add Drug. 4. Note the Find icon is not aligned correctly. | 2015-06-28T19:24:41.000-0400
28 | User Profile - Accessibility Report through WAVE | Attached are the accessibility reports from WAVE regarding the User Profile Page. To view this data in the actual application, do the following: 1. Navigate to http://wave.webaim.org/ 2. Input the desired page URL to ReX application and proceed. 3. View the results. | 2015-06-28T16:48:10.000-0400
29 | Drug Details - Accessibility Report through WAVE | Attached are the accessibility reports from WAVE regarding the Drug Details Page. To view this data in the actual application, do the following: 1. Navigate to http://wave.webaim.org/ 2. Input the desired page URL to ReX application and proceed. 3. View the results. | 2015-06-28T16:47:26.000-0400
30 | Add Drug - Accessibility Report through WAVE | Attached are the accessibility reports from WAVE regarding the Add Drug Page. To view this data in the actual application, do the following: 1. Navigate to http://wave.webaim.org/ 2. Input the desired page URL to ReX application and proceed. 3. View the results. | 2015-06-28T16:46:25.000-0400
31 | My Drug Cabinet - Accessibility Report through WAVE | Attached are the accessibility reports from WAVE regarding the My Drug Cabinet Page. To view this data in the actual application, do the following: 1. Navigate to http://wave.webaim.org/ 2. Input the desired page URL to ReX application and proceed. 3. View the results. | 2015-06-28T16:44:50.000-0400
32 | Sign Up - Accessibility Report through WAVE | Attached are the accessibility reports from WAVE regarding the Sign Up Page. To view this data in the actual application, do the following: 1. Navigate to http://wave.webaim.org/ 2. Input the desired page URL to ReX application and proceed. 3. View the results. | 2015-06-28T16:43:55.000-0400
33 | Sign In - Accessibility Report through WAVE | Attached are the accessibility reports from WAVE regarding the Sign In Page. To view this data in the actual application, do the following: 1. Navigate to http://wave.webaim.org/ 2. Input the desired page URL to ReX application and proceed. 3. View the results. | 2015-06-28T16:42:37.000-0400
34 | Landing Page - Accessibility Report through WAVE | Attached are the accessibility reports from WAVE regarding the Landing Page. To view this data in the actual application, do the following: 1. Navigate to http://wave.webaim.org/ 2. Input the desired page URL to ReX application and proceed. 3. View the results. | 2015-06-28T16:41:55.000-0400
35 | IE - Add Drug - When entering text in Search by Brand Name an X will appear at the end of the field but it is covered by search icon | When entering text on the Add Drug page in the Search by Brand Name field, the standard IE "x" appears to clear the text. Only problem is that it appears behind our search icon. See attached screenshot. Steps to reproduce: 1. Navigate to the application on IE 10 or 11. 2. Sign In. 3. Select Add Drug "+" icon. 4 .Enter text into the Search by Brand Name text box. 5. Note that our Search Icon will be over top of the "x" clear button. | 2015-06-28T15:00:56.000-0400
36 | Firefox/IE - Pixelated circle visible around Add Drug "+" icon or Close "X" icon | When viewing the Add Drug "+" icon or the close "X" icon in Firefox or IE, there is a visible circle going around the icon. See attached screenshot. Steps to reproduce: 1. Navigate to application. 2. Sign in. 3. Note there is a tiny visible circle around the "+" icon. | 2015-06-28T14:51:39.000-0400
37 | IE doesn't show drug names if they are more than one line long | Steps to reproduce 1) Login in Rex using IE 2) Go to my drug cabinet 3) Add a drug with more then one word in the name 4) Go back to my drug cabinet The drug name is blank See attachment showing same user in IE and Firefox | 2015-06-28T14:01:19.000-0400
38 | Add drug screen - 'X' in the search field using IE | When the user starts to type in the search field an X appears in the magnifying glass icon. Steps to reproduce 1)Login 2)go to My drug cabinet 3)Click on Add a drug 4)In the Add drug screen start typing anything in the search field An X appears in the magnifying glass. 5) Clean the field The X dissapears | 2015-06-28T13:47:50.000-0400
39 | Cabinet - "FIlter by brand name" in search field misplaced in IE11 | The writing "Filter by brand name" in the search field in the cabinet is too low and cut when using IE11 browser. Steps to reproduce: 1) Go to My drug cabinet 2)Take a look at the search field. The letters are misplaced 3) Write "aa" 4) Delete "aa" and click outside the field Now is shown properly | 2015-06-28T13:37:45.000-0400
40 | Add Drug at 320 pixel width (iphone 5) - Search icon displaying over top of text in search box | When viewing the Add Drug screen at a 320 pixel width (iphone 5 width), the search icon is displayed on top of the text in the search field. See attached screenshot. Steps to reproduce: 1. Navigate to application on iPhone 5 (or set browser to 320 pixel width). 2. Sign In. 3. Select Add Drug. 4. Note the Search icon is on top of the text. | 2015-06-28T13:28:08.000-0400
41 | Firefox - My Drug Cabinet - Text in "Filter by brand name" field is microscopic | When viewing the drug cabinet in Firefox browser, the text in "Filter by brand name" field is microscopic in size. You can enter data and it will remain at the very small size. Steps to reproduce: 1. Navigate to application on Firefox browser. 2. Sign In. 3. Note the text in "Filter by brand name" is microscopic. | 2015-06-28T12:52:39.000-0400
42 | Uses tab not underscored - Have to move to a different tab and back to see the underscore | The first tab in a drug details "Uses" is not underscored until user moves to other tab and back again. Steps to reproduce: 1) Go to cabinet. 2) Click in one drug 3) "Uses" is not underscored. 4) click on the next tab and back Now "Uses" is underscored Same happens in the "Add a Drug" screen | 2015-06-28T09:58:25.000-0400
43 | Add Drug Modal - On desktop browser, Notes field can be dragged and re-sized | When attempting to add a drug and receiving the Add Drug modal, it was found that the notes field could be expanded outside the modal window. See attached screenshot. Steps to reproduce: 1. Navigate to the application on a mobile device. 2. Sign in. 3. Select Add Drug button. 4. Search for a drug. 5. Tap on the drug name. 6. Tap Add to Cabinet button. 7. Add Drug modal will appear. 8. Notes field will have icon at the bottom right corner, click and drag the field outside of the modal. | 2015-06-26T17:19:09.000-0400
44 | Android/iOS - Delete Drug - Delete Drug button on modal is non-functional | When attempting to select the Add Drug button in the Add Drug Modal, it was found that the button does not function. Selecting the button does not add the drug nor does it dismiss the modal. Steps to reproduce: 1. Navigate to the application on a mobile device. 2. Sign in. 3. Select a drug that is in your inventory. 4. Select the Remove from Cabinet button. 5. Select Delete button. 6. Note that nothing will happen. | 2015-06-26T17:13:28.000-0400
45 | Android/iOS - Add Drug - Add Drug button on modal is non-functional | When attempting to select the Add Drug button in the Add Drug Modal, it was found that the button does not function. Selecting the button does not add the drug nor does it dismiss the modal. Steps to reproduce: 1. Navigate to the application on a mobile device. 2. Sign in. 3. Select Add Drug button. 4. Search for a drug. 5. Tap on the drug name. 6. Tap Add to Cabinet button. 7. Add Drug modal will appear. 8. Tap Add Drug button. 9. Note that nothing will happen. | 2015-06-26T17:11:24.000-0400
46 | Android/iOS - Add Drug - Expiration date and notes fields cannot be edited | When attempting to enter expiration date and notes data in to the Add Drug Modal, it was found that the fields could not be edited. Thus no data could be entered. Steps to reproduce: 1. Navigate to the application on a mobile device. 2. Sign in. 3. Select Add Drug button. 4. Search for a drug. 5. Tap on the drug name. 6. Tap Add to Cabinet button. 7. Add Drug modal will appear. 8. Tap into Expiration field or Notes field, note that you cannot enter any value. | 2015-06-26T17:05:12.000-0400
47 | Design Defects | -logos in header float all the way to left and right -button proportions are off (button bigger or icon smaller) and align it to the grid (right: 0) - consistent padding in top bandings (20px) -make header smaller and logo smaller on mobile cabinet: -more vertical padding in header Add-Drug - remove top-padding of 40 from banding Drug-details - lighter weight in p text | 2015-06-26T16:19:56.000-0400
48 | Design Updates | Landing Page - exactly like comp, except no logo: -gradient in header -patterned background -sign in button and asset -new buttons (6px border-radius) Inputs: b-r is 6 px buttons: 6px br (same color but solid), hover goes to darker teal cabinet: filter should be smaller and the 6px b-r drug-boxes: 1px border and 6px br get rid of the bottle on mobile and show the word recall when applicable drug name two lines Search: input change, new asset Search-results: new card line in card Not including: - new logo - depth in plus button | 2015-06-26T15:52:26.000-0400
49 | Drug Cabinet - Filter by Brand Drug Name is not working | When attempting to filter by Brand Drug name in the Drug Cabinet it was discovered that the filter is no longer working. Steps to reproduce: 1. Navigate to application. 2. Sign In. 3. Add a drug to cabinet if one does not exist already. 4. From Drug Cabinet, enter drug name into Filter by Brand Drug Name field. 5. Note that the filter will not work. | 2015-06-26T13:08:44.000-0400
50 | Drug Cabinet - Drugs with long running names are running outside of the drug cards | When adding drugs with long drug names to the cabinet, the text of the name is running outside of the card. See attached screenshot. Steps to reproduce: 1. Navigate to application. 2. Sign In. 3. Select Add Drug button. 4. Search for "Robitussin" 5. Select the Drug called "Robitussin Peak Cold Maximum Strength Cough Plus Chest Congestion DM" 6. Select Add to Cabinet. 7. Select X button to go back to cabinet. 8. Note the text of the drug is running outside of the card. | 2015-06-26T13:03:03.000-0400
51 | Add Drug - Warning tab showing "Uses" tab labels. | The warning tab in add drug is showing the correct information with wrong titles. See screen image, it works fine in cabinet but the bug is found when adding a new drug. Steps to reproduce: 1. Navigate to application. 2. Sign In. 3. Select Add Drug button. 4. Search for "Advil" 5. Select the first finding 6. Click on the "Warnings" tab. The titles are the same as the Uses tab but the paragraph information is correct. The tab is shown properly when reviewing the drug in the cabinet.. | 2015-06-26T13:00:22.000-0400
52 | Tab Titles | NA | 2015-06-26T10:49:46.000-0400
53 | Sign Up - No error message when email is incomplete | When an email is written without the ".com" or ".net" the error message disappears but still user is not able to sign up | 2015-06-26T09:09:19.000-0400
54 | Sign In - No alert given to user when login unsuccessful | When providing invalid credentials on the sign in page, no error message is given to the user, Acceptance criteria for EighteenF-1 says "I am alerted if login is not successful". Steps to reproduce: 1. Navigate to application. 2. Enter invalid username/password. 3. Select Sign In button. 4. Note user will not be alerted. | 2015-06-25T18:12:33.000-0400
55 | My Drug Cabinet - Recall text alignment is off at 1024p width | When viewing the drug cabinet at 1024p width, the Recall text is misaligned. See attached screenshot. Steps to reproduce: 1. Navigate to application. 2. Sign In. 3. Set your browser width to 1024p. (you can use chrome developer tools to do this) 4. Note the RECALL text is not aligned correctly. | 2015-06-25T15:49:37.000-0400
56 | Visual QA for the Recalls tab | There was a changes to the recalls tab during implementation that will require visual QA. | 2015-06-25T15:46:37.000-0400
57 | Handle "no data from API" in our proxy server and send appropriate response to front end | NA | 2015-06-25T14:49:55.000-0400
58 | Create Favicon | NA | 2015-06-25T14:46:20.000-0400
59 | As a user, I should be able to edit information about drugs in my cabinet | NA | 2015-06-25T14:22:10.000-0400
60 | "Hi <username" text is hidden on mobile device viewport sizes | When viewing any of the pages after signing in on a mobile device(where the username/profile button are displayed in the upper right hand corner), the text "Hi <username>" is no longer displayed. See attached screenshot. Steps to reproduce: 1. Navigate to application on mobile device (or resize browser to 320p width) 2. Sign In. 3. Note that the "Hi <username" text will not be visible, only the avatar. | 2015-06-25T12:21:57.000-0400
61 | Add Drug - "Go Back" from drug details does not take you back to search results, takes you to drug cabinet | When viewing the drug details after doing Add Drug search, selecting the Go Back link does not take you back to the search results. It will take you back to the drug cabinet. Steps to reproduce: 1. Navigate to the application. 2. Sign in. 3. Select Add Drug "+" button. 4. Search for tylenol. 5. Select a result. 6. Select Go Back link. 7. Note the user will not be taken back to the search results but will be taken back to the Cabinet. | 2015-06-25T12:16:36.000-0400
62 | Add Drug - Selecting any tab in Drug Details causes Add Drug panel (search field and button) to hide | When selecting into any of the drug details tabs (Uses, warnings, etc.), it causes the Add Drug panel located above to hide. Per the visual design comps, this panel should remain even when clicking through the different tabs. See attached screenshot. Steps to reproduce: 1. Navigate to application. 2. Sign In. 3. Select Add Drug "+" button. 4. Enter "Advil" and do a search. 5. Select one of the results to bring up drug details. 6. Note here that the Add Drug panel will still be present. 7. Select one of the drug detail tabs (uses, warnings, etc.) 8. Note now the Add Drug Panel above the details is hidden. | 2015-06-25T12:08:24.000-0400
63 | Add Drug - "+" Button should change to an "X" button s | When viewing the Add Drug page, the "+" button that was used to get there should change to an "x" button. See attached screenshot of the issue as well as the visual design comp. Selecting the "x" button should behave as the "+" currently behaves in this state and return the user to the drug cabinet. Steps to reproduce: 1. Navigate to application. 2. Sign in to the application. 3. Select the "+" button to Add Drug. 4. Note that the Add Drug page is displayed but the "+" button does not change to an "x" button. | 2015-06-25T11:59:08.000-0400
64 | Update copy | New copy provided from the copywriters in the comments of both attached PDFs. | 2015-06-25T09:56:23.000-0400
65 | View my profile information | NA | 2015-06-24T17:20:38.000-0400
66 | Sign In - Signup accepts emails longer than 70 characters but sign in doesn't | Is the user's email is longer than 70 characters the sign in process doesn't accept it and it doesn't show an error message. | 2015-06-24T15:52:40.000-0400
67 | Sign In on mobile - Spinner displayed can be moved off of the screen | When going through sign in on a mobile device (iOS or android) the spinner can be moved off of the screen. See attached screenshot. Steps to reproduce: 1. Navigate to web app on a mobile device (or degrade browser down to 320p width). 2. Select Sign In button. 3. Sign in to application. 4. Note the spinner will appear. 5. Scroll the spinner up/down off screen. | 2015-06-24T15:28:17.000-0400
68 | Sign In - Selecting Sign In button when email/password fields are blank results in infinite spinner | When going to the sign in page, selecting the sign in button when no data has been entered (no email or password) results in an infinite spinner being displayed. Steps to reproduce: 1. Navigate to the web application. 2. Select Sign In button to go to Sign In page. 3. Without putting in any information on the page, select Sign In button. 4. Note that the spinner will appear and the user will be stuck at this point. | 2015-06-24T15:24:50.000-0400
69 | Drug Cabinet - Cursor centered when clicking into Filter by Drug Name | When testing items in the drub cabinet page, selecting into the Filter by Drug Name field results in the cursor appearing centered in the field. See attached screenshot. Steps to reproduce: 1. Navigate to application. 2. Sign In with a valid user. 3. Click into the Filter by Drug Name field. 4. Note that the cursor will appear centered in the field. | 2015-06-24T14:45:24.000-0400
70 | Landing Page - Sign In / Sign Up options are not present at the top right corner per visual design | When viewing the landing page with the latest build, the sign in and sign up options are not present per the comps. See attached screenshot. Steps to reproduce: 1. Navigate to the site. 2. Note on the landing page that the sign in and sign up buttons in the upper right hand corner are not present per the comps. | 2015-06-24T14:33:38.000-0400
71 | Drug Cabinet - User first name is not displayed for profile in the upper right hand corner, currently "Hi Danny!" | After providing valid credentials and logging in, user is taken to the drug cabinet page. The user name that is displaying in the upper right hand corner is "Hi Danny". See attached screenshot. Steps to reproduce: 1. Launch application. 2. Sign in with valid email address. 3. Note that when taken to the drug cabinet, the profile name at the upper right is "Hi Danny!". Understanding that profiles have not been implemented yet, but if we don't have time than we need to display the email address of the user at the very least. | 2015-06-24T14:19:46.000-0400
72 | Drug Details - Strange gradient appearing on Safari and Firefox (desktop and mobile) on drug detail tabs | When viewing the Uses and Warnings tabs (these are the only ones available currently) on the drug detail page, you will note that there is a strange gradient that appears on Firefox and Safari (both mobile and desktop). See attached screenshot of Chrome on left and Firefox on right. Steps to reproduce: 1. Launch application on Safari or Firefox. 2. Sign in to application. 3. Select a Drug from the drug cabinet. 4. Note the strange gradient that appears on the page. 5. Note that this gradient will not appear for chrome. | 2015-06-24T14:03:18.000-0400
73 | Landing Page - Sign Up and Sign In button alignment is off when pixel width between 768 and 991 | When viewing the landing page with the resolution width being anywhere at or between 768 and 991, the sign up and sign in buttons are misaligned. See attached screenshots. Steps to reproduce: 1. Navigate to 18F landing page. 2. Change width of browser window to 769 or 991 (anything in between). NOTE: Chrome dev tools will allow you to set this value. 3. Note the misalignment of the sign up and sign on buttons. | 2015-06-24T11:59:36.000-0400
74 | Sign up - Message area blank when email is not complete | When the email lacks the '.com' or similar an error message area opens at the top of the window with no message in it.See attached document. | 2015-06-24T11:18:55.000-0400
75 | SIgn Up - Numbers are allowed in the first name field | The first name field in the sign up screen should be restricted to letters but it actually accepts numbers. | 2015-06-24T11:04:54.000-0400
76 | As a user, I can edit the expiration date for a drug in my cabinet | NA | 2015-06-23T15:15:19.000-0400
77 | As a user, I can delete a drug from my cabinet. | NA | 2015-06-23T15:09:51.000-0400
78 | As a user, I can filter by Brand Name and Active Ingredient | NA | 2015-06-23T09:44:36.000-0400
79 | As a user, I can filter drugs in my cabinet by name. | As the user types, drugs in the cabinet should be filtered by Brand Name. | 2015-06-23T09:37:33.000-0400
80 | Set up authentication based routing | NA | 2015-06-22T17:30:01.000-0400
81 | As a user, when I login for the first time I should be informed about the need to fill out my profile | After first-time sign up, the user will be taken to My Drug Cabinet page. The user should be presented with a modal informing them that we recommend that they complete their profile. | 2015-06-22T14:33:43.000-0400
82 | As a user, I can see which of the drugs in my cabinet have open/active recalls. | We will need to check the FDA API for recalls that match each drug in the inventory. Fields to check include: * status * report_date | 2015-06-22T13:24:09.000-0400
83 | As a user, I can filter drugs in my inventory by brand, active ingredient, and who is taking the drug. | NA | 2015-06-22T10:42:23.000-0400
84 | As a user, I should be able to select which family members are taking a particular drug. | When creating / editing a drug in my inventory, I should be able to select one or more members of my family that are taking the drug. (e.g. checkboxes) | 2015-06-22T10:29:40.000-0400
85 | As a user, I can share warnings (e.g. pregnancy information) via social media | NA | 2015-06-22T08:05:52.000-0400
86 | As a user, I can view a line chart of recalls over time for a drug in my inventory | NA | 2015-06-22T08:05:13.000-0400
87 | As a user, I can view a line chart of recent adverse effects for a drug in my inventory. | NA | 2015-06-22T08:04:16.000-0400
88 | As a user, I should be able to remove a drug from my cabinet. | When the user visits the view details screen, the user needs to be able to remove that particular drug from the inventory if needed. | 2015-06-21T09:07:05.000-0400
89 | As a user, if I or a family member is pregnant, an excerpt of pregnancy information is highlighted | When user visits the Drug Details screen, pregnancy information should be displayed regardless of the tab the user is looking at. This *ONLY* happens if the user is pregnant or if a member of the family is pregnant. Note: See attached for example excerpt from the wires. | 2015-06-21T08:54:48.000-0400
90 | As a user, I can view pregnancy information for any drug in my cabinet | When the user visits the Drug Details screen, information specific to pregnancy should presented on it's own tab. Pregnancy related fields from the FDA API include: *pregnancy_or_breast_feeding *pregnancy Note: this needs to be implemented with null exception handling in mind as we cannot guarantee the presence of data in the FDA API. If no data found, the tab should be displayed but indicate that pregnancy specific information is not available. | 2015-06-21T08:45:00.000-0400
91 | As a user, I can view warning information specific to prescription drugs for any prescription drug in my cabinet | When the user visits the Drug Details screen for a prescription drug, the warnings tab should be populated with the following fields from the FDA API: * warnings_cautions * adverse_reactions * box_warning * overdosage Note: we must implement this tab with null exception handling as we cannot guarantee the presence of these fields for every prescription drug. | 2015-06-21T08:26:35.000-0400
92 | As a user, I can view warning information specific to over the counter (OTC) drugs for any OTC drug in my cabinet | When the user visits the View Drug Details screen for an over the counter (OTC) drug, the warnings tab should be populated with information from the following API fields: * do_not_use * warnings * ask_doctor Note: we must implement this with null exception handling as we cannot guarantee that all OTC drugs will have information in all of the fields from the API. | 2015-06-21T08:20:08.000-0400
93 | As a user, I can view general details for any drug in my cabinet. | When the user clicks on an existing drug in the cabinet, the user should be presented with details for that particular drug. This includes both the user defined meta data (expiration, notes, family members) and information from the FDA API. This story represents the first tab on the View Drug Details screen. | 2015-06-21T08:08:35.000-0400
94 | As a new user, after I create an account, I should be guided through the basic features of the application. | The team discussed using a wizard approach that guides a new user user through setting up their profile and adding/searching for the first drug in their inventory. UX & Visual design to provide wires/comps. | 2015-06-21T07:56:12.000-0400
95 | As a user, I can view the published privacy policy for the site. | NA | 2015-06-21T07:49:51.000-0400
96 | As a user, I can manage general information in my profile | The user should be able to modify their location and credentials (username/password). | 2015-06-21T07:46:38.000-0400
97 | As a user, I can view details of a single drug I've added to my inventory. | View Drug Details is a collection of features that allow the user to explore details and warnings for a drug that's been added to the inventory. | 2015-06-21T07:32:15.000-0400
98 | As a user, I can view and manage my inventory. | "My Inventory" is a collection of features that enables the user to view and add drugs to their inventory. | 2015-06-21T07:28:49.000-0400
99 | As a user, I can view and manage my profile. | "My Profile" is a collection of features that help the user personalize their experience by adding family members, modifying geographic location, and managing credentials. | 2015-06-21T07:26:11.000-0400
100 | As a user, I expect to be able to create an account or login from the landing page. | NA | 2015-06-21T07:23:48.000-0400
101 | As a user, I visit the splash page before signing up or logging in to the system | The landing page should have basic information about the application: * Hero Image * Feature Overview * Instructions for getting started | 2015-06-21T07:21:06.000-0400
102 | As a user, I should be able to add expiration date information for a particular drug. | Additional *user defined* information includes: * Expiration date (date) | 2015-06-20T16:14:33.000-0400
103 | As a user, I should be able to add family members to my household. | NA | 2015-06-20T16:13:14.000-0400
104 | As a user, I should get a notification when one of the drugs in my inventory has expired. | NA | 2015-06-20T16:09:19.000-0400
105 | As a user, I would like to receive notifications when there is a new recall for one of the drugs in my inventory. | NA | 2015-06-20T16:08:40.000-0400
106 | As a user, I should be able to OCR a label for a new medication. | NA | 2015-06-20T16:08:11.000-0400
107 | As a user, I can view a basic overview of features on the landing page. | The landing page is the primary entry point for the system, visible to the public which does not require any authentication. | 2015-06-20T16:07:38.000-0400
108 | As a user, I should be able to view recent adverse reactions for a drug in my inventory. | NA | 2015-06-20T16:06:18.000-0400
109 | As a user, I can create a new password when I have forgotten my old one | NA | 2015-06-20T14:20:32.000-0400
110 | As a user, I can register for an account | NA | 2015-06-20T14:19:16.000-0400
111 | As a user, I can view a dashboard for drugs in my inventory so that I can quickly check for active recalls and other alerts associated with my inventory. | NA | 2015-06-20T10:12:56.000-0400
112 | As a user, I want to review current entries in my cabinet so that I can add/subtract entries at any time. | NA | 2015-06-20T10:12:47.000-0400
113 | As a user trying to add a new drug to my cabinet, I can search by active ingredient, brand name, or manufacturer before selecting an item to add to the inventory. | NA | 2015-06-20T10:12:35.000-0400
114 | As a user, I can add drugs to my existing cabinet so that I have complete visibility into the substances in my home. | NA | 2015-06-20T10:12:24.000-0400
115 | As a user, I can login to the application so I can manage family members and my drug cabinet securely. | NA | 2015-06-20T10:11:03.000-0400